## Sheet1
3
CSE312 Software Architecture: Principles and Practices
LAB CONTINUOUS EVALUATION SHEET
|  |  |  | 2005-08-01 | 2012-08-01 | 2019-08-01 | 2026-08-01 | 2002-09-01 | 2009-09-01 | 2016-09-01 | 2023-09-01 | 1930-09-01
SL.no | Project Title | Roll No | Name | WEEK1 | WEEK2 | WEEK3 | WEEK 4 | WEEK5(ASSIGNMENT+ QUIZ) | WEEK6 PROGRESS(% of Completion) + VIVA | WEEK7(FINAL REVIEW BEGINS) | WEEK8 | WEEK9 | GITHUB LINK | DOCUMENTATION LINK[ SRS, UML DIAGRAM, PPT, REPORTS etc..)
1 | RESUME ATS AUTOMATED SYSTEM | 2023BCS0171 | RAGHAV KRISHNA M | core workflow development of whole project + backend | backend+n8n and AI model training and prompt optimization | still developing backend | backend completed+final touches(clearing bugs) |  | Integrating Voice agent |  |  |  | https://github.com/RaghavEscada/HRautomation | https://drive.google.com/drive/folders/1FGqyKLZt9lZpYGNAxGyMomhefLZ3I02PP
2 |  | 2023BCS0099 | SURYA NARAYAN GHOSH | backend+API integration | integration of AI algorithms for parsing resume score | still developing backend | helping in frontend development |  | Debugging the AI automation |  |  |  | https://github.com/RaghavEscada/HRautomation
3 |  | 2023BCS0036 | HARIPRASANTH M | resume parsing functionality integration(database creation) | continuing work of week-1 and database development | working on frontend | developing testing strategies |  | Preparing SRS Document, PPT and connecting with Database |  |  |  | https://github.com/RaghavEscada/HRautomation
4 |  | 2023BCD0003 | NOOH K | PPT+frontend(design deveopment)+UML diagrams | finaized UI/UX design yet to start frontend | yet to Work | enhancing frontend |  | Debugging the Web App |  |  |  | https://github.com/RaghavEscada/HRautomation
5 | TURF-TRACK TURF MANAGEMENT SYSTEM | 2023BCD0024 | ASWIN PARAMES SS | Created basic backend functionalities (Node + express) | email validation using mailbox layer | otp verification using node mailer | Working on SMS notification |  | Email validation, Forgot password functionality ~85% of the project completed |  |  |  | https://github.com/Bichu0077/Turf-Track_fe , https://github.com/Bichu0077/Turf_Track_be
6 |  | 2023BCS0084 | ABIN V TOMY | Collected Data on Turf Locations | Admin profile UI and functions | User profile dashboard, Edit user data | User profile dashboard. wokring on secure authentication |  | User Profile bug fixes |  |  |  | https://github.com/Bichu0077/Turf-Track_fe , https://github.com/Bichu0077/Turf_Track_be
7 |  | 2023BCS0015 | RAVISHANKAR R | Booking Page UI and functions | Bug Fixes on booking and Receipt generation | Carousel Animation for Landing page | Booking page and Checkout page |  | Time slot picker and Checkout page |  |  |  | https://github.com/Bichu0077/Turf-Track_fe , https://github.com/Bichu0077/Turf_Track_be
8 |  | 2023BCS0102 | BICHU DEVNARAYAN | Frontend Template (React + Typescript) | Connected Database and added trail authentication (Supabase DB and Authentication) | Working on location filter API (OpenStreetMap) | Completed Location filter and other UI components |  | Profile Icon addition, Biiling and Reciept Generation |  |  |  | https://github.com/Bichu0077/Turf-Track_fe , https://github.com/Bichu0077/Turf_Track_be | https://drive.google.com/drive/folders/1blTzfU6uL8PDBgMeO0JyI5PxqL0Tm6He?usp=sharing
9 |  | 2023BCS0183 | AYSHA LINTHA | Designed Web UI (Figma) | User profile UI and functions | Payment Gateway Integration (Razorpay/stripe) | Payment Integration and Documentation |  | Presentation and SRS document |  |  |  | https://github.com/Bichu0077/Turf-Track_fe , https://github.com/Bichu0077/Turf_Track_be
10 | VEHICLE RENTAL SYSTEM | 2023BCS0003 | ADITYA GOPAL | Designing the UI | about and contact pages using react | Backend Framework using node | integrating frontend with backend |  | Connected with database |  |  |  | https://github.com/sm-bhuvan/vehicle_rental
11 |  | 2023BCS0198 | BHUVAN SM | Designing the UI | Landing and services pages using react | Enhanced UI | Updated frontend |  | Connected with database |  |  |  | https://github.com/sm-bhuvan/vehicle_rental | https://drive.google.com/drive/folders/1cKnQb7tS_350A-q2qLHtJZpHyBNS29Jr?usp=drive_link
12 |  | 2023BCS0222 | N MOHAMMED SUHAIL AHMED KHAN | SRS | Collected and managed data | setting up database | implementing features in backend using mongodb |  | Presentation and SRS document |  |  |  | https://github.com/sm-bhuvan/vehicle_rental
13 |  | 2023BCD0030 | R RANJITH KUMAR | Requirement analysis | vehicles page using react | Enhanced UI | Working on chatbot service |  | Integrating chatbot |  |  |  | https://github.com/sm-bhuvan/vehicle_rental
14 | RAILWAY RESERVATION SYSTEM | 2023BCS0081 | MAMALESH RAMANA RAJU | Made design prototypes for the project using figma | Improved the design for the project with bolt ai | Collected required data on trains using erail website | Collected data on fares and other issues on Indian Railways |  | Done Ppt on the project, Helped in making of seat selection Ui, Re-designed Passenger Profile. Completed ~ 65% |  |  |  | https://github.com/Mahhen/rtms | RTMS
15 |  | 2023BCD0027 | SUJAN GADDAM | Made a part of the system design | Developed database models using mongoose and node js | Implemented features using MongoDB Atlas for cloud-based data storage | Created UI for seat selection using Next.JS and Shadcn/TailwindCSS |  | Implemented the Seat Selection module by developing the frontend for seat choice and the backend for real-time seat availability updates. Completed ~ 65% |  |  |  | https://github.com/Mahhen/rtms
16 |  | 2023BCS0111 | MAHABUB MAHHEN NADINDLA | Made required documents for the project | Made home page for the users using next js | Provided authentication for the users uisng firebase and nodemailer | Created API and functions for web scraping Indian Railways API |  | Dealt with bugs in the backend and added cost feature for trains using node js Rescheduled trains according to their dates and fixed related backend issues. Completed ~ 65% |  |  |  | https://github.com/Mahhen/rtms
17 |  | 2023BCS0108 | MOHAMMED SABEEH | Made technical analysis on the project and suggested required tech stack to proceed | Made signup and login pages, also improved ui in the home page using next js and shad cn | Added functionalities which allows users to search PNR and trains using nodejs and next js | Created UI for Train Search page using Next.JS and TailwindCSS |  | Dealt with train search backend using nodejs. Added required functionalities for the search page. Completed ~ 65% |  |  |  | https://github.com/Mahhen/rtms
18 | AURICARE: A GIFT TO GOD'S CHILDREN | 2023BCS0237 | SIDHAARTH MOHANDAS | Deciding the topic for our Project and discussing the scope & feasibility of our project & about the code implementation (like whether we should do an agentic chatbot. should we implement tool calling etc) | Preparation of the sample patient & mock data which will serve as the general knowledge base for Autism from which chatbot will answer user queries using mockaroo & gemini (based on the different identified common symptoms of Autism Disorder) | Identifying various use-cases and possible questions that our system would need to address while scaling it up to a deployable system. Updating the SRS including the new changes brought about in our system. | Making changes to the SRS based on our recent developments. | Providing feedback on developing frontend & chatbot deployment onto frontend. Ensuring that all requirements are being met through regular discussions, changes to SRS. | Identifying the Software development procedure & identifying the suitable architecture for our project. (75 % completion) |  |  |  | https://github.com/sid7367/Auricare-V2.git | Software Architecture Project
19 |  | 2023BCD0066 | VENKAT CHIRANJEEVI | Setup and data collection. | Chatbot development with RAG ,GROQ API,LANGGRPAH,LANGCHIAN. | Deployment with Gradio UI. | Patient Side Chatbot Development | deployment with gradio UI | done integration and updated ui and completed 75% |  |  |  | https://github.com/venkatchiranjeevireddy/AUTISM_project | https://drive.google.com/drive/folders/1vzegJ4liuDU83IkDZ_u-mmo_zOvhJ4et?usp=sharing
20 |  | 2023BCS0231 | K. THARUN | Developed UI/UX for Features, Progress pages using React, Tailwind Css | Developed UI/UX for ChatBot, Resources, About and Team pages using React, Tailwind Css | Integrating Chatbot into Chatbot Page | chatbot integration in the doctor and patient page | implemented using flask and hugging face and chat interface with react ui and api and language integration | done integration and updated ui and completed 75% |  |  |  | https://github.com/Tharunkunamalla/Auricare-V2 | https://drive.google.com/drive/folders/1_uP5uau2t3iLSZD05xaPza5JKuMa_cpO?usp=drive_link
21 |  | 2023BCS0228 | B. SIVA SAI | Developed UI/UX for Features, Progress pages using React,Tailwind Css | Developed UI/UX for ChatBot,Resources, About and Team pages using React, Tailwind Css | Integrating Chatbot into Chatbot Page | Integrating Chatbot into Chatbot Page | implemented using flask and hugging face and chat interface with react ui and api and language integration | done integration and updated ui and completed 75% |  |  |  | https://github.com/sivasai1807/auricare-V2.git | https://docs.google.com/document/d/1Wl8OT6glRviSxJxxYqXzcO8tnGjRvV7u/edit?usp=drivesdk&ouid=111721607948869139737&rtpof=true&sd=true
22 | GYM MANAGEMENT SYSTEM | 2023BCS0096 | M.V.RAGHUPATHI SAI | Developed frontend:login page,dashboard | Connected backend with frontend templates | Connected database to the frontend | authorization of users (members,trainers,admin) |  | Done debugging in route files |  |  |  | https://github.com/yaswantsaiadapa/Gym_management_system_fitzone.git | https://drive.google.com/drive/folders/1yNvnLkWT9dOyi6yjDegA6ozYH8bORhsM?usp=sharing
23 |  | 2023BCS0030 | A.YASWANT SAI | Developed Backend: created a database using sqlite3 | Created Routes and models using Flask | Worked on backend functionalities | added more features in attendance and progress analytics |  | added extra features in model files |  |  |  | https://github.com/yaswantsaiadapa/gym_management_system_fitzone | https://drive.google.com/drive/folders/1yNvnLkWT9dOyi6yjDegA6ozYH8bORhsM?usp=sharing
24 |  | 2023BCS0075 | CH.VARUN CHOWDARY | Created base.html and used bootstrap for all templates | Created Frontend pages:Equipment status and list of equipment | Developed frontend: list of members.list of trainers | designed member dashboard and profile page |  | connection of fronted files with jinja templates |  |  |  | https://github.com/yaswantsaiadapa/gym_management_system_fitzone | https://drive.google.com/drive/folders/1yNvnLkWT9dOyi6yjDegA6ozYH8bORhsM?usp=sharing
25 |  | 2023BCS0039 | G.VISHNU VARDHAN | Made SRS document and ppt | Developed a page for membership renewal | Developed a page to mark attendance | designed trainer dashboard, diet plan and workout plans |  | debugging backend errors |  |  |  | https://github.com/yaswantsaiadapa/gym_management_system_fitzone | https://drive.google.com/drive/folders/1yNvnLkWT9dOyi6yjDegA6ozYH8bORhsM?usp=sharing
26 | AGRI CONNECT | 2023BCS0117 | ADARSH DUBEY | SRS and Features finalizing | Cloud DataBase Setup in supabase and backend project setup | developed User,booking ,registration entity | Connected forntend with backend ,dockerize the backend and deployed |  | Hosted database in cloud on neon postgreSql for easy aceess and used redux for state management |  |  |  | https://github.com/Gaurv007/AgriConnect | PorjectsDocumets
27 |  | 2023BCS0114 | GAURAV KUMAR | created figma base ui/ux design for project | project setup and react front end | completed frontend of project | working on Buy, Rent and AI assistant section for the project |  | create profile page,menue button and deployed the frontend |  |  |  | https://github.com/Gaurv007/AgriConnect | https://drive.google.com/drive/folders/1LaQjikCX--yf9zxzYF9-4bSgbut1MWNS?usp=sharing
28 |  | 2023BCS0120 | ANSH SINGH | Decided UI and Started Working on Chatbot | Connecting Chatbot to Vector Database Making it more functional for user | Adding Voice assistant to chatbot and Optional(making agentic Ai for paylater functionality) | Integrating AI Assistant with Frontened Using Fast Api and improving Chatbot response,Started Working on Paylater Agent |  | Connected Chatbot to frontened using Fast API and improve paylater agentic ai |  |  |  | https://github.com/Gaurv007/AgriConnect | https://drive.google.com/drive/folders/1LaQjikCX--yf9zxzYF9-4bSgbut1MWNS?usp=sharing
29 |  | 2023BCD0036 | AREPALLI GIREESH KUMAR GOWD | Created 3 Machine Learning Models for predicting the crop, yield, and price | Saving the models ,scalers,encoders, and created an interacticve user interface using streamlit | Creating the interface, improving model perfomance by cleaning data | Connecting ML models with streamlit interface and deploying it on streamlit cloud |  | model testing and integrating the models with the project |  |  |  | https://github.com/Gaurv007/AgriConnect | https://drive.google.com/drive/folders/1EsY8iFRpMCi50-ReY7w7q6ix9jNXyhj-?usp=sharing
30 |  | 2023BCS087 | JOSHI KSHITIJ SANTOSH | Reviewed requirements, prepared test plan outline, created documentation structure | Designed test cases, drafted user manual (installation/setup). | [7 empty] | https://github.com/Gaurv007/AgriConnect | https://drive.google.com/drive/folders/1LaQjikCX--yf9zxzYF9-4bSgbut1MWNS?usp=sharing
31 | EMERGENCY RESPONSE SYSTEM | 2023BCS0021 | GOURILAKSHMI S | Login page | Backend routes for authenciation | Dashboard for user | Twilio setup and Location co-ordinates setup |  | Admin login ,Voice assistant integration . Admin Dashboard and settings -- 80% PROJECT COMPLETED |  |  |  | https://github.com/medhashree05/EMERGENCY-RESPONSE-SYSTEM | ERS
32 |  | 2023BCS0051 | ADITHYA KRISHNA | Location setup for backend | Database (supbase) | Dashboard for admin | Profile page - data fetch and display |  | Call inetgration using Twilio,Admin and Emergencies table in supabase --80% PROJECT COMPLETED |  |  |  | https://github.com/medhashree05/EMERGENCY-RESPONSE-SYSTEM | ERS - Emergency response system
33 |  | 2023BCS0042 | N MEDHASHREE | Landing page | Profile page for user | Location page | Groq setup for Text chat |  | Location detection and alerting in chat and added modifications for chat history ,User dashboard (fetch and display) --80% PROJECT COMPLETED |  |  |  | https://github.com/medhashree05/EMERGENCY-RESPONSE-SYSTEM | EMERGENCY RESPONSE SYSTEM
34 |  | 2023BCS0156 | AMAL BYJU DEV | Package installations for frontend and backend | Backend routes for authenciation | Docker setup | Home Page - emergency call (PUT and GET) |  | Set address as emergency location and User profile complete integration ,PPT --80% PROJECT COMPLETED |  |  |  | https://github.com/medhashree05/EMERGENCY-RESPONSE-SYSTEM | https://drive.google.com/drive/folders/1BJep4UozIWiqltuvN2LwGCVGOYNPQuYG
35 |  | 2023BCS0048 | SEJAL SATHEESH | Registrations form for user | Reddis setup | Setting page | Login setup from database(User detection) |  | Send current location to selected emrgency contacts and search routes to respective locations,PPT --80% PROJECT COMPLETED |  |  |  | https://github.com/medhashree05/EMERGENCY-RESPONSE-SYSTEM | ERS
36 | SKILLAMIGO | 2023BCS0033 | AMAN KUMAR | SRS PREPARATION | UI DESIGN AND PAGE SETUP | FRONTEND WORK COMPLETE | Enhanced user interface for improved usability, responsiveness, and visual consistency. |  | Implemented apis for admin panel,made profile and gigs pages, design and implemented pages that are left.
37 |  | 2023BCS0027 | ASHISH RANJAN | DATABASE SETUP | BUILDING API | CONNECTING FRONTED TO BACKEND | Developed and optimized APIs, implemented database cleanup routines, and resolved parameter |  | Protected routes, implemented apis for profile and gig pages, |  |  |  |  | SKILLAMIGO
38 |  | 2023BCD0009 | SACHIN KUMAR GIRI | USER FLOW DESIGN AND LOCAL SETUP | AI AGENT SETUP | INTEGRATING AI BACKEND WITH FRONTEND | Implementing AI integration by connecting a FastAPI backend to a Next.js. |  | Implemented policy pipeline ,gigs automation and rag |  |  |  | GITUHB LINK : https://github.com/sachingiri01/SkillAmigo
39 |  | 2023BCS0177 | AJEET KUMAR | PAGE DESGIN | BUILDING API | CONNECTING FRONTED TO BACKEND | Developed and optimized APIs, implemented database cleanup routines, and resolved parameter |  | implemented apis, implemented cascading in database, improved security features.
40 | NETWORKX - 75% Project DONE | 2023BCD0006 | SHAUN ALAN JOSEPH | Setup backend, database, and Google OAuth. | Built backend APIs for profiles, follows, and messaging. | Connect the Profile Page UI to the backend APIs | Make followers page |  | Deployed the website to Vercel |  |  |  | GITHUB LINK - https://github.com/Venkat-jaswanth/NetworkX | Software Architecture - NETWORKX
41 |  | 2023BCS0054 | M.NIVIEN | Designed wireframes, wrote SRS document, and defined project styles. | Completed the final UI for the onboarding page. | Made the PPT for the project | Make new tables for posts |  | Updated the PPT with the new features |  |  |  | GITHUB LINK - https://github.com/Venkat-jaswanth/NetworkX | project
42 |  | 2023BCDC0021 | INDUPURU VENKAT JASWANTH | Created React project, login UI, and onboarding form. | Completed the main user interface shell with React Routing to allow navigation between pages. Backend | Build the functional Q&A page UI with React components and started working on Project Report | Connect APIs with posts ui and do react routing and Do loading animation Ui |  | Done with messaging service and UI ,implemted Profile page |  |  |  | GITHUB LINK - https://github.com/Venkat-jaswanth/NetworkX
43 |  | 2023BCS0135 | ARJUN KARTHIK KOMMIREDDY | Setup GitHub, Vercel deployment, and assisted with frontend components. | Designed and implemented the application's loading animations (loaders). | Finalize UI designs for Resource Hub and Interview Post pages | UI for Posts |  | designed ui for post card and profile card |  |  |  | GITHUB LINK - https://github.com/Venkat-jaswanth/NetworkX
44 |  | 2023BCD0018 | KESAVARAPU AKHIL | Connected frontend forms to backend API, setup basic routing. | Built backend APIs and database tables for all content. | Build backend APIs for all content (interviews, resources, Q&A) | APIs for posts |  | Implemented Services for the Posts,experinces functionality |  |  |  | GITHUB LINK - https://github.com/Venkat-jaswanth/NetworkX
45 | PROJECT MANAGEMENT APPLICATION (NEXUS) | 2023BCS0093 | VIDYA KAARTHIKA A | Backend Services For Login - node.js | Redux Toolkit Implementation | Team member addition slice and kanban board slice for redux using TypeScript | Testing (cypress, playwright) |  | 80 % of the project is completed |  |  |  | Frontend-https://github.com/MayankV004/Nexus-Frontend , Backend-https://github.com/MayankV004/Nexus-Backend | SA Project(NEXUS)
46 |  | 2023BCS0147 | ANOUSHKA SAMANTA | UML Diagrams,SRS, FrontEnd - Landing page,Login,Signup - Nextjs + TypeScript + Tailwind + ShadCn | Dashboard ,Project Page creation,Issue creation -frontend - Next.js+ TypeScript+Tailwind | Frontend for adding team members to a project and show progress in Kanban board - DND library | Bug identification |  | Tested with mock profiles |  |  |  | Frontend-https://github.com/MayankV004/Nexus-Frontend , Backend-https://github.com/MayankV004/Nexus-Backend | SA Project(NEXUS)
47 |  | 2023BCS0204 | MAYANK VERMA | BackEnd-Login,signup(Routes, Controllers, Server file) - Node.js , express | Backend for dashboard, project creation and issue creation - Node.js , Express | Backend routes for team member addition in project and Kanban board (Routes , Controllers) | Bug fixing |  | fixed backend bugs |  |  |  | Frontend-https://github.com/MayankV004/Nexus-Frontend , Backend-https://github.com/MayankV004/Nexus-Backend | SA Project(NEXUS)
48 |  | 2023BCD0012 | ARYAN PASALWAD | UML Diagrams,SRS | Axios configuration and UI/UX | Deployment of project - vercel and render, | Re deployment |  | Updated the PPT with the new features |  |  |  | Frontend-https://github.com/MayankV004/Nexus-Frontend , Backend-https://github.com/MayankV004/Nexus-Backend | SA Project(NEXUS)
49 |  | 2023BCS0186 | PRIYANSH GAUTAM | UI/UX designing for landing page and login/signup pages - figma | UI/UX designing and custom hooks | UI/UX for team member form and Kanban board - Figma | UI Responsiveness |  | Fixed ui inconsistencies |  |  |  | Frontend-https://github.com/MayankV004/Nexus-Frontend , Backend-https://github.com/MayankV004/Nexus-Backend | SA Project(NEXUS)
50 | ONLINE SHOPPING SYSTEM | 2023BCD0042 | SHIVAM KUMAR | SRS Document Creation | Login,Register and Landing Page | Made category , subcategory and products page | Cart Features | [5 empty] | https://github.com/shivam2718/Software-Architecture-project- | Online Shopping System
51 |  | 2023BCD0051 | KARTHIK P | Collected data and suggested tech stack | Made the controllers | Made components for uploading , editing and deleting products | Did my orders page | [5 empty] | https://github.com/shivam2718/Software-Architecture-project- | Online Shopping System
52 |  | 2023BCS0153 | VISHAL DHAWAL | Designing the UI | Email authentication for registrations and login | Made user page and subcategory page | Updated frontend for mobile compatibility | [5 empty] | https://github.com/shivam2718/Software-Architecture-project- | Online Shopping System
53 |  | 2023BCD0054 | TIPPANAWAR YASH SHITAL | Suggested project flow and ideas. | Made the basic routing for the website | Implemented middlewares | Updated Backend Features for cart | [5 empty] | https://github.com/shivam2718/Software-Architecture-project- | Online Shopping System
54 |  | 2023BCS0180 | SAYAND BABU | UML Diagram | Decided The Schemas Needed | Did paging for different pages of the website | Updated Backend Features for order | [5 empty] | https://github.com/shivam2718/Software-Architecture-project- | Online Shopping System
55 | ADVENTOURS:TOUR MANAGEMENT SYSTEM | 2023BCS0192 | RON STEPHEN MATHEW | Decided which all things to be done | UI For Home, Login, Signup,Pages in React | UI for Landing Page+Frontend in React | Created Profile page |  | Created Loading pages, Cards component to display tours [Project 80% complete] |  |  |  | https://github.com/NewtronReal/adventours | Adventours
56 |  | 2023BCS0195 | ADITHYA T J | Frontend setup (React js) | Created Routes folder to expose endpoints for the front-end to communicate with back-end | Added token handling login in the front-end for user authentication and management with context-api | Created Tour details page |  | Added popups, Footer [Project 80% complete] |  |  |  | https://github.com/NewtronReal/adventours-backend | Adventours
57 |  | 2023BCS0189 | DENZEL ROBIN | Suggested ideas for projects | Created diagrams | Created model folder and schema for the data with constraints | Added map feature, to navigate,locate sub stops using Mapbox. |  | Created Bookings page [Project 80% complete] |  |  |  | https://github.com/NewtronReal/adventours-backend | Adventours
58 |  | 2023BCS0201 | PRATHAM S KORE | Setup backend(node js) | made controller folder to manage, alter, retrive the data and other utility functions to send responses to frontend | Added Authentication logic in the backend using JWT and added secure and encrypted way to store sensitive data | Added payment feature using RazorPay |  | Deployment using azure, nginx. [Project 80% complete] |  |  |  | https://github.com/NewtronReal/adventours-backend | Adventours
59 |  | 2023BCS0225 | MUHAMMED MINHAJ P S | Create a PPT for Project Design | Made a README file for Complete System Details and created mongoDB cluster and hosted NoSQL database | created factory folder and unility functions for quick and easy usage for repeated tasks | Added SMTP mail feature using brevo for welcome email |  | Created Final presentation [Project 80% complete] |  |  |  | https://github.com/NewtronReal/adventours | Adventours
60 | TALENT PORTFOLIO MANAGEMENT SYSTEM | 2023BCS0168 | K HRISHITH | Backend Setup & Registration Page Api creation | Login Page and full Authentication Setup | Backend creation for file Posting setup | Backend setup |  | backend setup for user pages [80% complete] |  |  |  | https://github.com/vinuthna-11/TPMS | https://drive.google.com/drive/folders/1r4VfHwRT4Hpo2Jw2szRFgvyzfsBISX0I?usp=drive_link
61 |  | 2023BCS0069 | LAKSHMI HARSHITHA | UI for home,about us pages | UI for login,frontend | UI for profile page | UI for Posts |  | UI for talent users[80% complete] |  |  |  | https://github.com/vinuthna-11/TPMS | https://drive.google.com/drive/folders/1r4VfHwRT4Hpo2Jw2szRFgvyzfsBISX0I?usp=drive_link
62 |  | 2023BCS0150 | VINUTHNA | Backend Setup, working on email & Database Creation | Authentication Setup, frontend and backend connection | Backend creation for profile page | Backend setup |  | Project documentation[80% complete] |  |  |  | https://github.com/vinuthna-11/TPMS | https://drive.google.com/drive/folders/1r4VfHwRT4Hpo2Jw2szRFgvyzfsBISX0I?usp=drive_link
63 |  | 2023BCS0105 | M ROSHITHA | SRS document | Designed and implemented the registration page interface (frontend). | UI for Post Upload | Frontend updation |  | UI for scout users [80% complete] |  |  |  | https://github.com/vinuthna-11/TPMS | https://drive.google.com/drive/folders/1r4VfHwRT4Hpo2Jw2szRFgvyzfsBISX0I?usp=drive_link
64 | HOTEL MANAGEMENT SYSTEM (STAYSYNC) | 2023BCS0012 | ASWIN M | Prepared SRS | PPT drafting, UML diagrams | Razorpay - setup | Integrated AI chatbot utilising Gemini API, customised for responses on user and hotel data available in the system. | [5 empty] | https://github.com/mahadevpnair10/STAYSYNC | STAYSYNC - SOFTWARE ARCHITECTURE COURSE PROJECT
65 |  | 2023BCS0018 | MAHADEV P NAIR | Created User portal Homepage using React- Type Script. Consolidated functional requirements and implemented them for users in a scalable fashion | Created the Database and incorporated Needed tables for User Authentication in Mongo DB Atlas. Alongside them figured basic protoypes for booking cancellation predictor using existing ML models. | Created user and admin data management Logics using supabase and created corresponding database schemas for efficient and structured functioning . Shifted to SUPABASE for scalable solutions. | Completed the backend using Supabase , integrating serverless functions and data manipulating logics needed for user-admin functionalities. |  | Developed Booking management logic.Such that no overlaps occur between bookings. Updated the customer operations such as house keeping and room service request. |  |  |  | https://github.com/mahadevpnair10/STAYSYNC | STAYSYNC - SOFTWARE ARCHITECTURE COURSE PROJECT
66 |  | 2023BCS0063 | ZEWIN JOS | Login Page for Admin,Users using React and Tailwind. | User authentication with Supabase / Documentation of FrontEnd | Email OTP with Supabase Auth | Creeated database triggers and RLS policies for data integrity in Supabase. |  | Created Hotel Management/Creation form for admin integrating supabase backend and OpenStreetMap API for location gathering. |  |  |  | https://github.com/mahadevpnair10/STAYSYNC | STAYSYNC - SOFTWARE ARCHITECTURE COURSE PROJECT
67 |  | 2023BCS0024 | DIVON JOHN | Frontend-Admin portal | OpenStreetmap- Location Mangament | Hotel price prediction | Finishing frontend using react,integrated price prediction to frontemd |  | Using FastApi integrated the supabase,backend to the admins Frontend,so that prices on next 30 days can be seen to all admins |  |  |  | https://github.com/mahadevpnair10/STAYSYNC | STAYSYNC - SOFTWARE ARCHITECTURE COURSE PROJECT
68 | DISASTER MANAGEMENT SYSTEM | 2023BCS0129 | INCHARA M P | Sign in and Sign up - html,css | UI for Admin Dashboard - html, css | openstreetmap for location conversion | backend-flask -apis |  | sql to supabase, weather fetching - 80% completion of the project |  |  |  | https://github.com/idsaturn07/DISASTER_MANAGEMENT_SYSTEM | https://drive.google.com/drive/folders/1NBhBwnqeSQC8bs4HKSE9dJ_Xjq1A7z3D?usp=sharing
69 |  | 2023BCS0066 | DEEPANJALI TUDU | Sign in and Sign up - html, css | UI for User input - html, css | donor dashboard - html, css | medical - html, bootstrap5 |  | ppt, admin dashboard improvements(announcements, incident forwarding) |  |  |  |  | https://drive.google.com/drive/folders/1ZfN31o_FEjCax1EPcChD1m47Qs78Osdk?usp=drive_link
70 |  | 2023BCS0072 | ASIYA S | SRS | Alerts - js | started backend - python(flask) | shelters - html5, bootstrap5 |  | real time shelters availability fetching, real time hospitals nearby fetching- geocoding |  |  |  |  | https://drive.google.com/drive/folders/1-wgP8dX17HRzto4sF4iZaSFz70cHdcl-
71 |  | 2023BCS0126 | JADI HEMARUPINI | PPT | Sql | sql | incident reports and announcements |  | government dashboard, emergency dashboard |  |  |  |  | https://drive.google.com/drive/folders/1wC67-eF9RWiRBD470BeQiO1iqZvaBmMF?usp=sharing
72 | CHARITY DONATION MANAGEMENT SYSTEM | 2023BCS0165 | P.VADAN DATTA | MySQLWorkbench, few backend files, server.js, .env | rechecking all files, charitypage(js,css) | rechecking, updating database attributes of tables( user, campaign) | changed mysql to supabase doing profile pages and integrating stripe to the syatem, rechecking the final touch of whole project |  | updated our website, made the changes mam has told us to apply
73 |  | 2023BCS0207 | PRANEETHA PILLAI | login page(js,css) donor dashboard (js, css) | rechecking all files, fundraiserdashboard(js, css), many other required pages | rechecking, editing login page(js,css), landing page(js,css) | creating profile pages and rechecking all files |  | updated navbar, header |  |  |  |  | Major changes after final presentation are Like count for champaigns which is being used to prediction for the charities to reach their goal amount
74 |  | 2023BCS0234 | SRUJANA MEDABALIMI | register page(js,css) stripe installation, connecting stripe, campaginpage(js, css) | rechecking all files, landingpage(js,css), admindashboard(js,css), update payment method to razorpay, many other required pages | rechecking, updation of razorpaymethod, updation of donordashboard(js,css), admindashboard(js,css) | supabase integration and enhancing frontend and modifications |  | stripe integration, supabase integration, did database updated |  |  |  | code | CharityDonDocumentation and Demo
75 | STORE MANAGEMENT SYSTEM | 2023BCS0210 | AMIT KUMAR | Setup required tools and environments with pycharm, github and postman. | Developed login,register api, password change api,api connected with mongodb and tested using postman | Product api developed, category api developed and tested | Sales,Transaction Api intergrated as final and tested.Fixed bug related to database change.Chatboat searched to integrate in project.Searching for new feature to integrate as chatbaot for user . |  | Api of chatboat build, and tested and pushed [90+% project developed],searched for payment system building,auto sms system building to integrate as final to project |  |  |  | https://github.com/Rohit-Pratap-Singh-Tech/Store-Management-System/tree/main/Backend | https://drive.google.com/drive/folders/11CLEp4nngX_J6CQuHmvXYaYiQUDvUbWj?usp=sharing
76 |  | 2023BCS0138 | ROHIT PRATAP SINGH | Setup required tools and environment for frontend development. | Developed Login, Signup, and Landing Page with responsive design and user-friendly interface. | Developed Dashboard UI for all actors (Admin, Manager, Inventory Manager, Cashier) and implemented the interactive 2D store map to visually highlight product locations. | Integrating dashboards with live API endpoints, testing role-based features, fixing UI bugs, refining overall user experience, and connecting the 2D store map with backend. |  | Progress -> 90%, AI chatbot connected, Store Navigation Fix, minor issues fixed,Payment system add |  |  |  | https://github.com/Rohit-Pratap-Singh-Tech/Store-Management-System.git | https://drive.google.com/drive/folders/11CLEp4nngX_J6CQuHmvXYaYiQUDvUbWj?usp=sharing
77 |  | 2023BCD0015 | BHASKARA AKSHAY SRIRAM | Set up and ran the frontend Vite development server, troubleshooting initial npm and directory issues | Implemented glassmorphism effects using backdrop-filter, hover animations, and consistent styling throughout the application | Refined the BillingProcessPage to seamlessly blend with the Hero background instead of appearing as separate section | Integrating dashboards with live API endpoints, testing role-based features, fixing UI bugs, refining overall user experience, and connecting the 2D store map with backend. |  | Made minor changes in the dashboard, Fixed some bugs and the Store Navigation system |  |  |  | https://github.com/Rohit-Pratap-Singh-Tech/Store-Management-System.git | https://drive.google.com/drive/folders/11CLEp4nngX_J6CQuHmvXYaYiQUDvUbWj?usp=sharing
78 |  | 2023BCS0219 | CHENNUPATI BHARGAV | set up the required tools and environment for database using mongodb | creating database and linking it with the backend | inserting the required data of different categories of staff and different information of products available in the store | Database Schema updated for location,Bug fix related to connection between api datatype and database datatype. Making SRC document. Making Class diagram. | [5 empty] | https://github.com/Rohit-Pratap-Singh-Tech/Store-Management-System.git | https://drive.google.com/drive/folders/11CLEp4nngX_J6CQuHmvXYaYiQUDvUbWj?usp=sharing
79 | MUSIC STREAMING APPLICATION(NoteZ) | 2023BCD0033 | N.LALITH CHAITANYA | Set up project structure (React frontend + Node.js backend). | Added PlayLists,profiles,Albums operations in backend. | Created Moldel for Recommendations of songs | Created database triggers for data integrity in Supabase. |  | fixed public , private playlist bugs (75% completed) |  |  |  | https://github.com/pmjp1509/NoteZ.git | SA
80 |  | 2023BCS0123 | P MUNI JYOTHI PRAKASH | Create backend with Node.js/Express (basic routes for notes). | Connect frontend with backend APIs (fetch, save notes). | Integrate chatbot using HuggingFace API (sentiment/emotion detection for our app). | Integrating dashboards with live API endpoints,fixing UI bugs, refining overall user experience |  | created profile and search bar fetchs(75% completed) |  |  |  | https://github.com/pmjp1509/NoteZ.git | SA
81 |  | 2023BCS0039 | YASWANTH SAI G | Setup Supabase Storage & Athuntication(tables for users, music) | Implement authentication (signup, login, JWT). | Added advanced features (note search, filters, AI suggestions). | Created Profile page |  | bottom player UI,logic and authentication bug fix(75% completed) |  |  |  | https://github.com/pmjp1509/NoteZ.git | SA
82 |  | 2023BCD0063 | D.UDAY KIRAN | Design UI screens (login, signup, dashboard, note editor). | UI/UX designing for user dashboard | Polished UI/UX (dark mode, responsive design, user-friendly chatbot interface). | favorite page bug fixes |  | working friend request's and content creator page(75% completed) |  |  |  | https://github.com/pmjp1509/NoteZ.git | SA
84 | RESTAURANT MANAGEMENT SYSTEM | 2023BCS0159 | T. SAI KARTHIK | DESIGNED ORDER AND ANALYTICS PAGE | SQL data table entries and cordinating as per front end | connected backend and SQL templates(bridging) | Debugging Inventory page and dashBoard |  | Reverified Feedback Bias of object models(Completed 75%) |  |  |  | https://github.com/pmashubb2005-cell/RESTAURANT-MANAGEMENT-SYSTEM-GOLDEN-FEAST- | https://drive.google.com/drive/folders/1iHdpzjI2LKzxrn7h6huzBRsuWF1EiuwY?usp=drive_link
85 |  | 2023BCS0162 | V. BALAJI BHARGAV | Done SRS & UML Diagrams | Done backend devolopement in landing pages,setup,login ,sign up pages | worked on functionalities,defining routes and flask modeling | Front-end and Back-end of Analytics page |  | Debugged Staff page and Analytics page Anomalies(Completed 75%) |  |  |  | https://github.com/pmashubb2005-cell/RESTAURANT-MANAGEMENT-SYSTEM-GOLDEN-FEAST- | https://drive.google.com/drive/folders/1iHdpzjI2LKzxrn7h6huzBRsuWF1EiuwY?usp=drive_link
86 |  | 2023BCD0045 | K. SAI NIHAL | Done frontend on landing page,signup,signin,initial dashboard framework | partial assistance in sql enforcing part,data enhancements in inventory and analytics pages | worked on dashboard features (specialised) real time dynamic tracker of franchise restaurant | Modifying and Debugging login page |  | Modifying and Finalizing SRS, Project PPT(Completed 75%) |  |  |  | https://github.com/pmashubb2005-cell/RESTAURANT-MANAGEMENT-SYSTEM-GOLDEN-FEAST- | https://drive.google.com/drive/folders/1iHdpzjI2LKzxrn7h6huzBRsuWF1EiuwY?usp=drive_link
87 |  | 2023BCS0174 | PETA MASHUB | Done Front- end of Home page | Front-end of Menu, Inventory, order pages | order tracking,implementation of intermediate mediumwares, | Debugging order page, Menu page |  | integrated datasets in cordination (MVC) object model and view cordination(Completed 75%) |  |  |  | https://github.com/pmashubb2005-cell/RESTAURANT-MANAGEMENT-SYSTEM-GOLDEN-FEAST- | https://drive.google.com/drive/folders/1iHdpzjI2LKzxrn7h6huzBRsuWF1EiuwY?usp=drive_link
| HOSPITAL MANAGEMENT SYSTEM(HospiTrack) | 2023BCD0060 | AMEES A.N | Design patient & doctor database schema | Connect DB with Flask backend later changed to desktop app | Optimize DB queries & security | bug fixes in UI |  | completed 90% of the project |  |  |  | https://github.com/kalyankoushik181-lab/HospiTrack.git | https://drive.google.com/drive/folders/154LZ4N6ut0JX-gDgQq-2YqsRtV9y1KAY
88 |  | 2023BCS0144 | DHARAVATH ANVESH | Build appointment module | Appointment booking UI (Flask + PyQt5) | Add admin dashboard for appointments | Prescription and medical record Triggers |  | created setup file |  |  |  | https://github.com/kalyankoushik181-lab/HospiTrack.git | https://drive.google.com/drive/folders/154LZ4N6ut0JX-gDgQq-2YqsRtV9y1KAY
89 |  | 2023BCS0090 | KARTHIK RAMAVATH | Develop billing/payment structure | Integrate billing UI & DB | Improve recommendation system with patient history | fixed background image issue |  | created PPT |  |  |  | https://github.com/kalyankoushik181-lab/HospiTrack.git | https://drive.google.com/drive/folders/154LZ4N6ut0JX-gDgQq-2YqsRtV9y1KAY
90 |  | 2023BCS0213 | DHANUSH BABU | Prescription history module | Prescription history tracking UI | Prescription export/reporting feature | payment gateway integration |  | fixed booking appointments issue |  |  |  | https://github.com/kalyankoushik181-lab/HospiTrack.git | https://drive.google.com/drive/folders/154LZ4N6ut0JX-gDgQq-2YqsRtV9y1KAY
91 |  | 2023BCS0216 | KALYAN KOUSHIK | Set up project structure (flask,). | Implement basic doctor/medicine recommendations | created Billing page | fixed JSON data passage issue |  | fixed search bar in medical records page |  |  |  | https://github.com/kalyankoushik181-lab/HospiTrack.git | https://drive.google.com/drive/folders/154LZ4N6ut0JX-gDgQq-2YqsRtV9y1KAY
94 | TRADEBRIDGE (STUDENT RENTAL SYSTEM) | 2023BCS0009 | ROSHAN BINOJ | Decided the pages required for the website and folder structure | Frontend template | Product cards created | Integration of Frontend |  | Did Deployment of the Project on Vercel and 85% of project is completed |  |  |  | https://github.com/roshanbinoj-iiitk/TradeBridge | https://drive.google.com/file/d/17eRJr-koZLErTBdWHDtayJkB-B_G0rLc/view?usp=sharing
95 |  | 2023BCS0045 | NIKHIL KUMAR | Came up with the idea, functional and non functional requirements | Started Admin Functionality | Implementation of Admin | Integration of Admin |  | Done with the Admin Page |  |  |  | https://github.com/roshanbinoj-iiitk/TradeBridge | https://drive.google.com/file/d/1XtmytUN-_dJi83B15ejl_TKiVnV9m8hJ/view?usp=sharing
96 |  | 2023BCS0057 | VISHWANATH DARUR | SRS Document | Worked on documentation | Documentation | Documented the projects report |  | Created PPT and Documentation |  |  |  | https://github.com/roshanbinoj-iiitk/TradeBridge | https://drive.google.com/file/d/1c4lXw7_iDv_Ltp9Qapy-FbFVZo9yFPD0/view?usp=sharing
97 |  | 2023BCS0132 | MOHAMMED SIRAJUDHEEN | UML Diagram creation | Backend template | Added for tables for implementing the features | Integration of Backend |  | Fine Tuned the Backend |  |  |  | https://github.com/roshanbinoj-iiitk/TradeBridge | https://drive.google.com/file/d/18Ol1B2gJ3FeIr9il2MCKkxF5X5GXBAzz/view?usp=sharing
98 | UNIFOOD-CANTEEN FEEDBACK AND PRE-ORDERING SYSTEM | 2023BCS0060 | NIKKATH ZABEEN SHAIK | prepared srs , login page , react js | created frontend componens for student dashboard , react js | created components for manager dashboard , react js | implemented analytics in manager dashboard |  | Refined student frontend components, 90% done |  |  |  | https://github.com/pavan-charan/Unifood.git | Building-a-Smarter-Canteen-Ordering-and-Feedback-System.pdf , SRS_Unifood.pdf
99 |  | 2023BCS0078 | S S PAVAN CHARAN | installed dependencies and set up the environment , vs code ,github | implemented callback functions , node js , supabase auth | refined the entire frontend and backend till date , react, node | connected student and manager dashboards |  | Refined manager frontend components, 90% done |  |  |  | https://github.com/pavan-charan/Unifood.git | Building-a-Smarter-Canteen-Ordering-and-Feedback-System.pdf , SRS_Unifood.pdf
100 |  | 2023BCD0057 | YASWANTH SAI B | environment and designed database structure, supabase | maintained student dashboard crud opertaions , supabase | maintained manager dashboard crud opertaions , supabase , node | Documented the projects report |  | Checked the database communications, 90% done |  |  |  | https://github.com/pavan-charan/Unifood.git | Building-a-Smarter-Canteen-Ordering-and-Feedback-System.pdf , SRS_Unifood.pdf
101 |  | 2023BCD0048 | SHIVADEEPAK S | created backend api structure | rest api backend implemented for some endpoints | implemented some core endpoints for manager component , ,node | integrating payment functionality |  | Adjusted the backend functions, 90% done |  |  |  | https://github.com/pavan-charan/Unifood.git | https://drive.google.com/file/d/12KslVyd8pEL4CbsT4lRUOywa3w2SmyGg/view?usp=drivesdk , https://drive.google.com/file/d/1SW3ubLmm99rMwC2IJ5rJP3fwujZ-C4oy/view?usp=sharing
103 | SAVR: SMART VALUE-BASED RETAIL DELIVERY SYSTEM | 2022BCS0153 | BARUKULA BRIJESH BENAAYAAH | Prepared uml diagrams | worked on frontend using react.js | completed 60% work on front end used react.js, html, css(tailwind). | Studied about the documentation and modified database according to the requirements |  | Completed the documentation and ppt |  |  |  |  | https://drive.google.com/drive/u/2/folders/1WY2RW_Rt3DBiSUQ9AH29N7HzUQDz4JQv
104 |  | 2023BCS0141 | LOKESH B | Prepared uml diagrams, installed all softwares | Cretead a clean working database using MySql | complete designing database and working on backend using django(python) | Completed the backend and making adjustments for the necessary requirements |  | Finalized all of the backend and the database integration. Fixed all the debugging errors. |  |  |  | https://github.com/Balaga-Lokesh/SAVR | https://drive.google.com/drive/u/2/folders/1WY2RW_Rt3DBiSUQ9AH29N7HzUQDz4JQv
105 |  | 2023BCS0006 | HAFIZ FEROZ | Prepared SRS | worked on frontend using react.js | integrating frontend to backend used react.js | Integraded the updated backend with the frontend and enhanced the user interface |  | Completed all the frontend parts and completed integration of changes with the backend |  |  |  |  | https://drive.google.com/drive/u/2/folders/1WY2RW_Rt3DBiSUQ9AH29N7HzUQDz4JQv